## Roles & Resources
Role | Name | FTE % | Estimated Hours | Skill Level | Main Responsibilities
Project Manager | Bella Grimaldo | 25% | 140 | Intermediate | Project planning, scheduling, buget, risk, and communication
Frontend Developer | Jazmine More | 75% | 420 | Intermediate | User dashboard, interactive maps, reservation screen and filters
Backend Developer | Sarah Yi | 75% | 420 | Advanced | Parking availability, reservations, payments, and database operations
UI/UX Designer | Daniel Hernandez | 30% | 168 | Intermediate | Interface designs, navigation, and user experience
QA Tester | Selena Gomez | 40% | 224 | Intermediate | Feature testing, integration, and defect reporting
DevOps Engineer | Ryan Morgan | 20% | 112 | Intermediate | Cloud infrastructure, deployment, and system monitoring
Assuming: 14 weeks * a 40 hr week = 560 full time hours.
560 hrs * FTE - Estimated Hours

## Resource Plan
Role | Name | FTE % | Estimated Hours | Hourly Rate | Total Cost
Project Manager | Bella Grimaldo | 25% | 140 | 45 | 6300
Frontend Developer | Jazmine More | 75% | 420 | 40 | 16800
Backend Developer | Sarah Yi | 75% | 420 | 50 | 21000
UI/UX Designer | Daniel Hernandez | 30% | 168 | 35 | 5880
QA Tester | Selena Gomez | 40% | 224 | 30 | 6720
DevOps Engineer | Ryan Morgan | 20% | 112 | 45 | 5040
Total |  |  | 1484 |  | 61740

## Cost Plan
Cost Estimate
Item | Category | Quantity/Duration | Unit Cost | Total
Employee Labor | Labor | 1,484 hours | Varies | 61740
Cloud Hosting | Infrastructure | 4 months | $150/month | 600
Software Licenses | Tools | One-time | 300 | 300
Maps/API Services | Third-party APIs | 4 months | $100/month | 400
Testing Tools | Tools | One-time | 200 | 200
Subtotal |  |  |  | 63240
contingency reserve | reserve | 10% of subtotal |  | 6324
Total Project Budget |  |  |  | 69564
Monthly Budget Cashflow
Month | Labor | Other Expenses | Contingency | Total
September | 12000 | 450 | 1245 | 13695
October | 20000 | 350 | 2035 | 22385
November | 21000 | 350 | 2135 | 23485
December | 8740 | 350 | 909 | 9999
Total | 61740 | 1500 | 6324 | 69564

## RACI Matrix
Task/Deliverable | Project Manager | Frontend Developer | Backend Developer | UI/UX Designer | QA Tester | DevOps Engineer
Requirements gathering | A/R | C | C | C | C | I
UI/UX Design | C | C | I | A/R | C | I
System Architecture & Database | I | C | A/R | I | C | C
Frontend Development | I | A/R | C | C | C | I
Backend Development | I | C | A/R | I | C | C
Parking Availability and Reporting | I | R | A/R | C | C | I
Reservations & Payments | I | R | A/R | C | C | I
Testing & QA | I | C | C | I | A/R | C
Deployment | I | C | C | I | C | A
Documentation | A/R | C | C | C | C | I
Final Presentation & Closure | A/R | I | I | I | C | I