## Risk Register
Risk ID | Risk Description | Probability | Impact | Owner | Response Strategy | Status/Notes
R1 | Real time parking availability could be wrong | 3-Moderate | 4-Major | Development Team | Mitigate | Monitor and test real time availability data for accuracy
R4 | The login system could fail to authenticate users correctly or deny acces even with the correct cradentials | 2 - Low | 4 - Major | Development Team | Mitigate | Test authentication and login functionality to ensure users can access their accounts
R5 | A project task could take longer to complete than originally estimated | 4 - High | 3 - Moderate | Project Manager | Mitigate | Monitor task progress and adjust the schedule if delays occur
R7 | New requirements or features could be added during the project making it difficult to meet the planned deadline | 2- Low | 3 - Moderate | Project Manager | Accept | Monitor for changes and adjust the schedule if needed
R9 | Services or software tools could cost more than originally budgeted | 2 - Low | 1 - Negligible | Project Manager | Accept | Monitor service and software costs throughout the project
R13 | The departure of a team member could cause delays or incomplete work | 2- Low | 4 - Major | Project Manager | Mitigate | Reduce the impact o a team member leaving by correctly documenting their work and making sure responsibilities can be reassigned
R14 | Poor comunication amoung the team | 3 - Moderate | 3 - Moderate | Project Manager | Mitigate | Establish regular meetings and clear communication methods
R10 | Equipment like sensor cost could be higher than originally estimated | 2 - Low | 1 - Negligible | Project Manager | Accept | Monitor equipment and sensor costs throughout the project
R15 | Lack of technical skills among team members could cause mistakes or project delays | 2 - Low | 3 - Moderate | Project Manager | Mitigate | Provide training or additional support to team members when needed
R3 | Navigation could fail to guide users correctly | 3 - Moderate | 4 - Major | Development Team | Transfer | Use a reliable third-party navigtaion funcionality
R17 | Users could report incorrect parking availability information, causing inaccurate parking space status updates | 3 - Moderate | 3 - Moderate | Development Team | Mitigate | Validate user-submitted parking reports and require operator review before changing parking availability
R18 | Errors when modifying reservations could result in incorrect parking availability or conflicting bookings | 2 - Low | 4 - Major | Development Team | Mitigate | Test reservation modifications to ensure parking availability is updated correctly and double bookings are prevented

## Risk Identification
Risk ID | Category | Description
R1 | Technical | Real time parking availability could be wrong
R2 | Technical | The interactive map could display incorrect information
R3 | Technical | Navigation could fail to guide users correctly
R4 | Technical | The login system could fail to authenticate users correctly or deny acces even with the correct cradentials
R5 | Schedule | A project task could take longer to complete than originally estimated
R6 | Schedule | A delay in one task could cause dependent tasks to start later than planned
R7 | Schedule | New requirements or features could be added during the project making it difficult to meet the planned deadline
R8 | Schedule | A project phase could take longer than planned and cause delays
R9 | Financial | Services or software tools could cost more than originally budgeted
R10 | Financial | Equipment like sensor cost could be higher than originally estimated
R11 | Financial | Delays could result in additional labor or development costs
R12 | Financial | Maintenance and operating costs could be higher than estimated
R13 | People | The departure of a team member could cause delays or incomplete work
R14 | People | Poor comunication amoung the team
R15 | People | Lack of technical skills among team members could cause mistakes or project delays
R16 | People | Conflict between team members could slow decision-making and delay project tasks
R17 | Technical | Users could report incorrect parking availability information, causing inaccurate parking space status updates
R18 | Technical | Errors when modifying reservations could result in incorrect parking availability or conflicting bookings

## Communication Plan
Report | Frequency | Method | Participants | Purpose
Team Stand-up | Twice a week | Microsoft Teams | Project Manager and Development Team | Discuss progress, blockers, and upcoming tasks
Weeky Project Status Report | Weekly | Email | Project Manager and Stakeholder | Summarize project progress, risks, and upcoming goals
Development Progress Meeting | Weekly | Microsoft Teams | Project Manager and Development Team | Review completed work and track progress toward project milestones
Feature Demo Meeting | At the end of each major project phase | Microsoft Teams | Project Manager, Development Tean, and Stakeholders | Demonstrate completed features and gather stakeholder feedback